Project PRISM — 2026 Enterprise Project Plan

Predictive Risk & Intervention Simulation Model

Target Outcome:
Establish PRISM as Acentra Health’s enterprise decision intelligence platform for identifying not just who is high risk, but who is most likely to benefit from intervention at scale.

### Core Capabilities

PRISM is built on six core capabilities:

- Baseline Risk Modeling

- Intervention Impact Estimation

- Counterfactual Outcome Estimation

- High-Value Subgroup Identification

- Alternative Strategy Simulation

- Explainability

### Enterprise Priorities

The focus for 2026 is to operationalize these capabilities through:

- Enterprise data engineering

- Scalable feature engineering

- Production-ready modeling pipelines

- Multiple outcome frameworks

- Governance and model monitoring

- Operational integration

PROJECT PRISM — ACCELERATED ENTERPRISE ROADMAP (MAY 2026 – DEC 2026)

Predictive Risk & Intervention Simulation Model

Strategic Goal:

Deliver the first enterprise-grade PRISM release by September 2026, followed by advanced causal/simulation capabilities and expanded outcome models by December 2026.

Legend:

█ = Active Work

▓ = Major Milestone / Go-Live

▒ = Stabilization / Optimization – this one is not actually used in the roadmap.

A cleaner, R-generated version of the roadmap tables was saved in the same folder:

“PRISM Project Plan roadmap.pdf”.

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM / PHASE                           MAY JUN JUL AUG SEP OCT NOV DEC

-------------------------------------------------------------------------------------------------------------------

PROGRAM GOVERNANCE & STRATEGY

Project Charter & Governance                ███

Executive Sponsorship Alignment             ███

Success Metrics / KPI Definition            ███

Steering Committee & Reporting              ████████████████████████

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM A — DATA & FEATURE ENGINEERING

Enterprise Data Inventory                   ███

Canonical Member Timeline                   █████

Historical Intervention Mapping             █████

Feature Store Design                        ████

Clinical Feature Engineering                █████████

SDOH Feature Engineering                    ██████████

Behavioral / Engagement Features            ██████████

Temporal Feature Engineering                ██████████

Data Quality & Validation                   █████████████

Reusable Pipeline Development               █████████████

Feature Lineage Documentation                  ███████

MILESTONE: FEATURE STORE V1                                     ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM B — BASELINE PREDICTIVE MODELING

Outcome Variable Prioritization             ███

ED Utilization Model Development            ███████

Admission Risk Model Development            ███████

High-Cost Escalation Model                  ██████

Rising Risk Identification Model            ██████

Validation Framework                        ███████

Calibration & Threshold Testing                ██████

Performance Benchmarking                      ██████

Explainability Layer (SHAP)                   ████████

MILESTONE: CORE MODELS VALIDATED                                 ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM C — AUTOMATION & MLOPS

Automation Architecture Design                 ████

Automated Scoring Pipelines                      ███████

Model Retraining Pipelines                        ███████

Monitoring & Drift Detection                      ███████

Version Control & Auditability                    ███████

Production Scheduling                               █████

MILESTONE: AUTOMATED MODEL OPERATIONS                             ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM D — UI / PRODUCTIZATION (LENS)

LENS Requirements & UX Design               ███

Wireframes & Dashboard Design                  █████

Risk Prioritization Dashboard                    ███████

Explainability Dashboard                        ███████

Simulation Dashboard                               ███████

Subgroup Explorer                                   ██████

UAT & Stakeholder Feedback                      ███████

MILESTONE: PRISM LENS RELEASE V1                               ▓

MILESTONE: ADVANCED PRISM UI                                                         ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM E — GOVERNANCE & COMPLIANCE

Model Governance Framework                  ████

Audit & Reproducibility Standards              ██████

Bias / Equity Review                            ██████

Clinical SME Validation                         ███████

Documentation & SOP Development                    ████████

MILESTONE: GOVERNANCE PACKAGE COMPLETE                                             ▓

-------------------------------------------------------------------------------------------------------------------

PHASE 1 — SEPTEMBER 2026 DELIVERY

(FOUNDATIONAL INTELLIGENCE ENGINE)

Deliverables:

• Enterprise feature store

• Automated scoring pipelines

• ED utilization prediction model

• Admission prediction model

• High-cost escalation model

• Explainability layer

• LENS dashboard v1

• Initial intervention opportunity scoring

• Initial operational pilot

GO-LIVE: SEPTEMBER 2026                                        ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM F — ADVANCED CAUSAL & UPLIFT MODELING

Treatment / Control Cohorts                           ████

Uplift Modeling Development                           ███████

Meta-Learners (T/X/DR)                                ███████

Counterfactual Estimation                             ███████

Individual Treatment Effects                          ███████

Causal Forests / HTE Modeling                           ███████

Subgroup Optimization                                   ██████

Sensitivity & Robustness Testing                        ███████

MILESTONE: ADVANCED CAUSAL MODELS                                                ▓

-------------------------------------------------------------------------------------------------------------------

WORKSTREAM G — SIMULATION ENGINE

Simulation Framework Design                           ████

Alternative Strategy Engine                           ███████

ROI / Cost Avoidance Logic                            ███████

Policy Simulation Modeling                             ███████

Scenario Optimization                                  ███████

Strategy Comparison Framework                          ███████

MILESTONE: SIMULATION ENGINE LIVE                                              ▓

-------------------------------------------------------------------------------------------------------------------

PHASE 2 — DECEMBER 2026 DELIVERY

(ADVANCED INTERVENTION INTELLIGENCE)

Deliverables:

• Uplift modeling

• Counterfactual estimation

• Individual treatment effects

• High-value subgroup optimization

• Simulation engine

• Alternative strategy testing

• ROI simulation capability

• Expanded outcome model portfolio

• Advanced PRISM dashboard suite

GO-LIVE: DECEMBER 2026                                                                  ▓

-------------------------------------------------------------------------------------------------------------------

OUTCOME MODEL DELIVERY SCHEDULE

FOUNDATIONAL MODELS (SEPT 2026)

90-Day ED Prediction Model                █████████▓

90-Day Admission Prediction Model         █████████▓

High-Cost Escalation Model                ████████▓

Rising Risk Identification                ████████▓

ADVANCED MODELS (DEC 2026)

Readmission Prediction Model                          ███████▓

Avoidable Admission Model                            ███████▓

Medication Adherence Model                           ███████▓

Quality Gap Closure Prediction                       ███████▓

Behavioral Health Escalation                         ███████▓

SDOH Instability Prediction                          ███████▓

KEY EXECUTIVE MILESTONES

MAY 2026

• Project kickoff

• Governance established

• Data architecture finalized

JUNE 2026

• Canonical datasets established

• Feature engineering underway

• Baseline modeling initiated

JULY 2026

• Core predictive models operational

• Explainability framework integrated

• Initial LENS development complete

AUGUST 2026

• UAT and pilot readiness

• Automated scoring pipelines operational

• Dashboard integration testing

SEPTEMBER 2026 — PHASE 1 GO-LIVE

▓ PRISM foundational release operational

OCTOBER 2026

• Begin uplift & causal modeling

• Counterfactual framework development

• Simulation engine development

NOVEMBER 2026

• Advanced subgroup optimization

• Strategy simulation testing

• Expanded outcomes integrated

DECEMBER 2026 — PHASE 2 GO-LIVE

▓ Full PRISM intervention intelligence platform operational

-------------------------------------------------------------------------------------------------------------------

ACCELERATED DELIVERY RISKS

1. Feature engineering bottlenecks

2. Intervention data normalization complexity

3. LENS development bandwidth

4. Model validation compression

5. SME availability for rapid iteration

-------------------------------------------------------------------------------------------------------------------

CRITICAL SUCCESS FACTORS

• Strong ETL + Data Science coordination

• Early governance establishment

• Strict scope management for Sept release

• Parallel workstreams

• Prioritize operationally valuable models first

• Reusable feature engineering architecture

• Automation-first mindset

-------------------------------------------------------------------------------------------------------------------

1. Recommended Delivery Strategy

You should treat PRISM as three staggered programs, not one monolithic model.

Program 1 — Foundation & Core Prediction Layer

Target Completion: September 30, 2026

This establishes:

- enterprise feature store,

- core pipelines,

- baseline predictive infrastructure,

- first production-ready outcome models,

- initial simulation framework,

- explainability layer.

This becomes the “minimum viable intelligence engine.”

Program 2 — Advanced Causal/Uplift Modeling

Target Completion: November 2026

Adds:

- treatment effect estimation,

- counterfactuals,

- subgroup optimization,

- intervention targeting optimization.

Program 3 — Enterprise Expansion Models

Target Completion: December 31, 2026

Adds:

- additional outcome domains,

- additional service lines,

- production governance,

- reusable modeling framework.

2. Recommended Outcome Variables (Staggered)

You are correct that these should have different timelines.

Phase 1 Outcomes (September 2026)

These are operationally achievable first.

| Outcome | Complexity | Reason |
| --- | --- | --- |
| 90-Day ED Visit | Moderate | Strong signal availability |
| 90-Day Inpatient Admission | Moderate | Clear claims-based outcome |
| High-Cost Escalation | Moderate | Important for ROI |
| Rising Risk Identification | Moderate | Supports proactive CM |

These align well with your POC narrative around ED optimization.

Phase 2 Outcomes (Nov–Dec 2026)

| Outcome | Complexity | Notes |
| --- | --- | --- |
| Readmission Risk | Higher | Temporal complexity |
| Avoidable Admission | Higher | Clinical definition complexity |
| Medication Nonadherence | Higher | Pharmacy integration |
| Quality Gap Closure Probability | Higher | HEDIS integration |
| Behavioral Health Escalation | Higher | Data availability variability |
| SDOH Instability Prediction | Advanced | Requires enrichment strategy |

3. Enterprise Architecture Workstreams

You are essentially building five parallel tracks.

WORKSTREAM A — Data Engineering & Feature Store

(Largest Lift)

Timeline

Jan 2026 – July 2026

This is likely 40–50% of total effort.

Key Deliverables

A1. Canonical Member Timeline

Build longitudinal member structure:

- claims

- encounters

- interventions

- assessments

- pharmacy

- SDOH

- eligibility

- provider interactions

A2. Feature Store

Build reusable engineered variables:

Clinical Features

- Chronic conditions

- Comorbidity indices

- Risk trajectories

- Episode counts

- Utilization intensity

Intervention Features

- Program enrollment

- Touch frequency

- Call duration

- Outreach cadence

- Engagement duration

- Opt-out behavior

SDOH Features

- Housing instability

- Transportation barriers

- Food insecurity proxies

- Geographic deprivation

Behavioral Features

- Engagement consistency

- Missed appointments

- Outreach responsiveness

A3. Temporal Engineering

Critical for PRISM success.

Examples:

- rolling 30/60/90 day windows

- utilization acceleration

- intervention timing effects

- “time since last ED”

- “engagement decay”

Deliverables

- Enterprise feature dictionary

- Feature lineage documentation

- Reusable feature pipelines

- Data quality scorecards

WORKSTREAM B — Modeling Infrastructure

Timeline

March 2026 – September 2026

Phase 1 Models

B1. Baseline Predictive Models

Models:

- Gradient Boosting

- XGBoost

- LightGBM

- Logistic Regression benchmark

As outlined in your PRISM methodology slides.

B2. Validation Framework

Required Metrics

Classification

- AUC/ROC

- Precision/Recall

- F1

- Calibration

- Top decile lift

Business Metrics

- PMPM capture

- ED capture rate

- Intervention efficiency

- Number needed to engage

B3. Explainability Layer

You already identified SHAP-based explainability.

Deliver:

- local explanations

- global explanations

- feature importance

- member-level narratives

- clinician-friendly interpretation layer

WORKSTREAM C — Causal & Uplift Modeling

Timeline

July 2026 – November 2026

This is the true differentiator of PRISM.

C1. Uplift Modeling

As shown in your POC:

- estimate intervention impact,

- identify members who benefit most.

Models:

- Two-model uplift

- Transformed outcome

- Causal boosting

C2. Meta-Learners

You already identified:

- T-Learners

- X-Learners

- DR-Learners

Use for:

- counterfactual estimation

- individualized treatment effects

C3. Causal Forests

For subgroup discovery.

Deliver:

- high-value subgroup identification

- treatment heterogeneity analysis

- equity-sensitive targeting

WORKSTREAM D — Simulation Engine

Timeline

August 2026 – December 2026

This becomes the executive “what-if” layer.

Simulations

Operational

- What if we target top 5% vs 10%?

- What if intervention occurs earlier?

- What if staffing changes?

Financial

- PMPM savings

- avoided admissions

- avoided ED visits

- intervention ROI

Strategic

- compare targeting strategies

- estimate impact before deployment

This directly aligns with your “Simulate Alternative Strategy” methodology.

WORKSTREAM E — Productization & Operationalization

Timeline

May 2026 – December 2026

E1. PRISM UI / LENS Integration

Phase 1 (Sept 2026)

- risk prioritization dashboard

- intervention opportunity score

- explainability summaries

Phase 2 (Dec 2026)

- simulation dashboard

- subgroup explorer

- intervention optimization tools

E2. Automation

Move from:
manual extraction

To:
scheduled enterprise workflows:

- automated scoring

- automated retraining

- automated validation

- monitoring dashboards

E3. Governance

Needed for enterprise credibility.

Deliverables

- model governance framework

- drift monitoring

- retraining standards

- audit trail

- versioning

- reproducibility documentation

4. High-Level Timeline

Q1 2026 — Foundation & Design

January

- Project kickoff

- Governance established

- Outcome prioritization

- Architecture finalized

February

- Data inventory

- Feature engineering design

- Historical intervention mapping

- Define validation methodology

March

- Build canonical datasets

- Begin feature store

- Initial baseline modeling

Q2 2026 — Core Engineering & Baseline Models

April

- Complete feature pipelines

- Initial ED model

- Initial admission model

May

- Validation framework

- Calibration/testing

- Explainability integration

June

- Initial LENS wireframes

- Automation design

- Model refinement

Q3 2026 — Phase 1 Production Release

TARGET: September 30, 2026

July

- Productionize ED model

- Productionize admission model

- UAT begins

August

- LENS integration

- Automated scoring

- Pilot testing

September

PHASE 1 GO-LIVE

Deliver:

- ED prediction

- Admission prediction

- Risk prioritization

- Explainability layer

- Initial simulation framework

Q4 2026 — Advanced Intelligence Layer

October

- Uplift modeling

- Counterfactual estimation

- Intervention effect estimation

November

- Causal forests

- High-value subgrouping

- Simulation optimization

December

PHASE 2 GO-LIVE

Deliver:

- advanced causal models

- intervention optimization

- simulation engine

- additional outcomes

- enterprise reporting package

5. Team Structure Recommendation

| Role | Suggested Allocation |
| --- | --- |
| Product Owner (You) | 0.5–0.75 |
| Senior Data Scientist | 1.0 |
| Data Scientist | 1.0 |
| ETL Engineer | 1.0 |
| Analytics Engineer | 0.5 |
| LENS/Power BI Developer | 0.5 |
| Clinical SME | 0.25 |
| Report Engineering | 0.25 |
| DevOps/MLOps | 0.25 |

6. Critical Success Factors

Most Important

1. Feature Engineering Quality

This will matter more than algorithm sophistication.

2. Intervention Data Integrity

PRISM’s differentiator is:
“Did intervention actually change the outcome?”

You must accurately capture:

- intervention timing,

- intensity,

- engagement,

- completion,

- opt-out behavior.

3. Temporal Consistency

Avoid leakage:

- no future information,

- proper retrospective windows,

- intervention timing controls.

4. Explainability

Especially for Medicaid clients and clinicians.

Your SHAP + LLM explanation layer is strategically smart.

7. Recommended Success Metrics

By Sept 2026

- Automated feature pipelines operational

- ED and admission models live

- AUC > 0.75 target

- Explainability operational

- LENS dashboard deployed

- Pilot client operational

By Dec 2026

- Uplift models operational

- Simulation engine operational

- Counterfactual estimation live

- Multiple outcome domains supported

- Governance framework complete

- Enterprise-ready scalability